## How to use
Renovation budget
A budget for a renovation or a build: plan the costs, compare quotes and keep track of what you really spend.
How to use it
1 | On the Settings sheet name the project, set the reserve in % and adjust the list of rooms (stages) and categories.
2 | On the Items sheet add every item: room, category, quantity, unit and unit price. The plan is calculated.
3 | As bills come in, write the real cost and mark whether it is paid.
4 | On the Quotes sheet compare up to three contractors item by item — the cheapest price is highlighted.
5 | The Overview sheet shows plan vs. actual by room, the reserve and what is left to pay.
Yellow cells are for you to fill in.
White cells calculate themselves (they are protected so you don't overwrite a formula — Review → Unprotect sheet, no password).
Tips
• Delete the example rows (a bathroom) before you start.
• Ask for quotes with the same list of work so they can be compared.
• Keep the reserve aside — don't plan it for extras.
Free template from Planmero · planmero.com/en/renovation-budget-excel/

## Settings
Project settings
On the Settings sheet name the project, set the reserve in % and adjust the list of rooms (stages) and categories.
Project | Bathroom and kitchen renovation
Reserve (%) | 15%
Rooms / stages |  | Categories
Bathroom |  | Material
Kitchen |  | Labour
Living room |  | Transport
Bedroom |  | Waste removal
Children's room |  | Design and permits
Hall |  | Other
Toilet
Electrics
Plumbing and heating
Windows and doors
Floors
Facade and roof

## Items
Items
On the Items sheet add every item: room, category, quantity, unit and unit price. The plan is calculated. As bills come in, write the real cost and mark whether it is paid.
Room / stage | Category | Item | Quantity | Unit | Unit price | Plan | Actual | Difference | Paid | Supplier | Note
Bathroom | Material | Wall tiles | 24 | m² | 28 | 672 | 652 | -20 | Yes | Tile shop |  | 0
Bathroom | Material | Floor tiles | 6 | m² | 35 | 210 | 210 | 0 | Yes | Tile shop |  | 0
Bathroom | Material | Tile adhesive and grout | 12 | bag | 14 | 168 | [5 empty] | 168
Bathroom | Material | Shower tray and screen | 1 | pc | 540 | 540 | [5 empty] | 540
Bathroom | Material | Washbasin with cabinet | 1 | pc | 380 | 380 | [5 empty] | 380
Bathroom | Material | Toilet (wall-hung, with frame) | 1 | pc | 420 | 420 | [5 empty] | 420
Bathroom | Labour | Demolition | 1 | job | 450 | 450 | 450 | 0 | Yes | Builder |  | 0
Bathroom | Labour | Tiling | 30 | m² | 32 | 960 | [5 empty] | 960
Bathroom | Labour | Plumbing | 1 | job | 650 | 650 | [5 empty] | 650
Bathroom | Waste removal | Skip for rubble | 1 | pc | 180 | 180 | [5 empty] | 180
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Quotes
Contractor quotes
Enter the price each company quotes for the same work. The cheapest price in each row is highlighted.
Work | Company A | Company B | Company C
Demolition | 450 | 520 | 400
Tiling (30 m²) | 960 | 1050 | 900
Plumbing | 650 | 600 | 720
Electrics | 380 | 420 | 350
Total | 2440 | 2590 | 2370
Cheapest in total | Company C

## Overview
Budget overview
The Overview sheet shows plan vs. actual by room, the reserve and what is left to pay.
Plan | Reserve | Plan with reserve | Actual | Paid | Left to pay
4630 | 694.5 | 5324.5 | 1312 | 1312 | 3298
Room / stage | Plan | Actual | Difference | Paid | Left to pay
Bathroom | 4630 | 1312 | -20 | 1312 | 3298
Kitchen | 0 | 0 | 0 | 0 | 0
Living room | 0 | 0 | 0 | 0 | 0
Bedroom | 0 | 0 | 0 | 0 | 0
Children's room | 0 | 0 | 0 | 0 | 0
Hall | 0 | 0 | 0 | 0 | 0
Toilet | 0 | 0 | 0 | 0 | 0
Electrics | 0 | 0 | 0 | 0 | 0
Plumbing and heating | 0 | 0 | 0 | 0 | 0
Windows and doors | 0 | 0 | 0 | 0 | 0
Floors | 0 | 0 | 0 | 0 | 0
Facade and roof | 0 | 0 | 0 | 0 | 0
Total | 4630 | 1312 | -20 | 1312 | 3298
Category | Plan | Actual
Material | 2390 | 862
Labour | 2060 | 450
Transport | 0 | 0
Waste removal | 180 | 0
Design and permits | 0 | 0
Other | 0 | 0